## B04 Sprint 1
|  |  | Story 2 | task 1 | task 2 | task 3 | task 4 | task 5 | Story 3 | task 1 | task 2 | task 3 | task 4 | task 5 | Story 10 | task 1 | task 2 | task 3 | task 4 | task 5
|  | Responsibility |  | Rishab Tiwari | Satyam Kumar | Satyam Shubham | Shubham Mangal | Utsav Singh |  | Rishab Tiwari | Satyam Kumar | Satyam Shubham | Shubham Mangal | Utsav Singh |  | Rishab Tiwari | Satyam Kumar | Satyam Shubham | Shubham Mangal | Utsav Singh
Plan | Actual | Story Estimate | Story 2: 15; Story 3: 15; Story 10: 30
60 | 60 | 2017-09-19 |  | 2 | 4 | 0 | 4 | 5 |  | 3 | 0 | 4 | 5 | 3 |  | 7 | 4 | 4 | 10 | 5
40 | 49 | 2017-09-23 |  | 1 | 4 | 0 | 3 | 4 |  | 3 | 0 | 4 | 4 | 3 |  | 6 | 2 | 3 | 8 | 4
40 | 48 | 2017-09-26 |  | 1 | 4 | 0 | 3 | 4 |  | 3 | 0 | 4 | 4 | 3 |  | 6 | 2 | 3 | 8 | 3
40 | 48 | 2017-09-30 |  | 1 | 4 | 0 | 3 | 4 |  | 3 | 0 | 4 | 4 | 3 |  | 6 | 2 | 3 | 8 | 3
20 | 31 | 2017-10-02 |  | 1 | 3 | 0 | 2 | 3 |  | 2 | 0 | 2 | 2 | 2 |  | 4 | 1 | 2 | 5 | 2
0 | 6 | 2017-10-05 |  | 0 | 2 | 0 | 0 | 1 |  | 0 | 0 | 1 | 0 | 0 |  | 1 | 0 | 0 | 0 | 1

## B04 Sprint 2
|  |  | Story 1 | task 1 | task 2 | task 3 | task 4 | task 5 | Story 4 | task 1 | task 2 | task 3 | task 4 | task 5 | Story 6 | task 1 | task 2 | task 3 | task 4 | task 5
|  | Responsibility |  | Rishab Tiwari | Satyam Kumar | Satyam Shubham | Shubham Mangal | Utsav Singh |  | Rishab Tiwari | Satyam Kumar | Satyam Shubham | Shubham Mangal | Utsav Singh |  | Rishab Tiwari | Satyam Kumar | Satyam Shubham | Shubham Mangal | Utsav Singh
Plan | Actual | Story Estimate | Story 1: 25; Story 4: 35; Story 6: 40
100 | 100 | 2017-10-06 |  | 5 | 2 | 3 | 10 | 5 |  | 8 | 5 | 5 | 10 | 7 |  | 5 | 5 | 5 | 15 | 10
80 | 86 | 2017-10-10 |  | 4 | 1 | 3 | 8 | 4 |  | 6 | 4 | 5 | 9 | 5 |  | 4 | 5 | 5 | 14 | 9
80 | 81 | 2017-10-13 |  | 3 | 1 | 2 | 6 | 3 |  | 6 | 4 | 5 | 9 | 5 |  | 4 | 5 | 5 | 14 | 9
80 | 81 | 2017-10-17 |  | 3 | 1 | 2 | 6 | 3 |  | 6 | 4 | 5 | 9 | 5 |  | 4 | 5 | 5 | 14 | 9
55 | 57 | 2017-10-20 |  | 3 | 1 | 2 | 6 | 3 |  | 3 | 2 | 3 | 7 | 3 |  | 2 | 3 | 2 | 10 | 7
40 | 35 | 2017-10-23 |  | 1 | 0 | 1 | 2 | 2 |  | 2 | 1 | 2 | 5 | 2 |  | 1 | 2 | 1 | 8 | 5
20 | 18 | 2017-10-27 |  | 0 | 0 | 0 | 1 | 1 |  | 1 | 0 | 1 | 3 | 1 |  | 0 | 1 | 0 | 6 | 3
0 | 7 | 2017-10-31 |  | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 1 | 1 | 0 |  | 0 | 0 | 0 | 2 | 2

## B04 Sprint 3
|  |  | Story 5 | task 1 | task 2 | task 3 | task 4 | task 5 | Story 7 | task 1 | task 2 | task 3 | task 4 | task 5 | Story 8 | task 1 | task 2 | task 3 | task 4 | task 5 | Story 9 | task 1 | task 2 | task 3 | task 4 | task 5
|  | Responsibility |  | Rishab Tiwari | Satyam Kumar | Satyam Shubham | Shubham Mangal | Utsav Singh |  | Rishab Tiwari | Satyam Kumar | Satyam Shubham | Shubham Mangal | Utsav Singh |  | Rishab Tiwari | Satyam Kumar | Satyam Shubham | Shubham Mangal | Utsav Singh |  | Rishab Tiwari | Satyam Kumar | Satyam Shubham | Shubham Mangal | Utsav Singh
Plan | Actual | Story Estimate | 25 | [5 empty] | 25 | [5 empty] | 25 | [5 empty] | 25
100 | 100 | 2017-10-31 |  | 5 | 2 | 3 | 10 | 5 |  | 3 | 5 | 5 | 7 | 5 |  | 5 | 4 | 4 | 9 | 3 |  | 4 | 4 | 3 | 8 | 6
80 | 78 | 2017-11-03 |  | 4 | 1 | 2 | 8 | 4 |  | 2 | 4 | 4 | 6 | 4 |  | 4 | 2 | 3 | 7 | 2 |  | 4 | 3 | 3 | 6 | 5
65 | 61 | 2017-11-07 |  | 3 | 1 | 1 | 6 | 3 |  | 1 | 3 | 4 | 5 | 3 |  | 3 | 1 | 2 | 7 | 2 |  | 3 | 3 | 2 | 4 | 4
50 | 50 | 2017-11-10 |  | 2 | 0 | 1 | 6 | 2 |  | 0 | 2 | 3 | 5 | 3 |  | 2 | 0 | 2 | 7 | 1 |  | 3 | 3 | 1 | 4 | 3
35 | 34 | 2017-11-14 |  | 1 | 0 | 0 | 6 | 1 |  | 0 | 1 | 2 | 2 | 3 |  | 1 | 0 | 2 | 5 | 1 |  | 2 | 2 | 1 | 2 | 2
20 | 14 | 2017-11-17 |  | 0 | 0 | 0 | 2 | 0 |  | 0 | 0 | 1 | 0 | 2 |  | 0 | 0 | 1 | 3 | 0 |  | 0 | 2 | 0 | 2 | 1
0 | 0 | 2017-11-21 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0